KVANN HEALTH — Long-Term Strategic Roadmap

Version: 1.1.0 · Date: 2026-09-14 · Owner: Alexey (Technical Lead), with Joe (Medical) & Jaime (Sales)

Source: KVANN_HEALTH_STRATEGIC_VISION_MCKINSEY.md (Sept 2026) · Horizon: 36 months

Corporate Entity: KVAN Health LLC (Oregon) · Commercial Brand: Kvann Health / Kvann Flow

Primary Domains: `kvanhealth.com` and `kvannhealth.com` (cross-redirect)

North Star

Build the first closed-loop **Autonomous Ambulatory Operating System** for US primary care:

**Access (Intake) → Yield (Scheduling) → Audit (Chart QA)** — sold modularly, priced

disruptively ($149/MD/mo entry for Pillar 2, scaling to ~$499/MD/mo for the full suite),

with the "Iron Rule" (write-back restricted to Appointments

only) as the enterprise trust anchor.

36-month target: ~3,000 practices, ~$54M ARR, NRR > 130%, churn < 2%.

*All financial figures (ARR, ROI, pricing) in this document are modeled projections from the

Strategic Vision source document, presented for planning purposes — not guarantees of

performance. They must be re-validated against pilot results before external or investor use.*

Phase Architecture (3 Horizons)

HORIZON 1 — LAND: "Trojan Horse Scheduler" (Months 1–6)

Product: Kvann Flow (Pillar 2 — Capacity & Schedule Optimizer) ONLY.

Why first: zero clinical workflow disruption; fastest security clearance; provable ROI

($178k/yr per 5-MD clinic from Gravity Stacking alone).

| Workstream | Milestones | Exit Criteria |
| --- | --- | --- |
| Product | Epic sandbox integration hardened (fix JKU/JWKS + scope findings); mock client; production infra (FastAPI/Gunicorn/Docker) | Passes a "skeptical CIO" technical diligence |
| Pilot | CCC pilot (Pareto scope: Gravity Stacking + Lunch Firewall for 2–3 volunteer providers, staff-facing only) | ≥8% schedule density improvement, zero safety incidents, 90-day referenceable case study |
| GTM | Athenahealth Marketplace (MDP) + Epic Connection Hub registration | Listed / in review |
| Corporate | LLC finalized (KVAN Health LLC), domains (`kvanhealth.com` + `kvannhealth.com`) + email live, basic website | Domains operational, email active |
| Funding | Accelerator applications (Tier 1: OVF; Tier 2: Cedars-Sinai, Mayo) | ≥1 acceptance or term sheet |

Pricing: $149/MD/mo entry. Target: 3 signed pilot clinics + 50 qualified practice pipeline by Month 6 exit; $2.2M ARR run-rate across ~250 practices by Month 12 (Year 1 Exit).

HORIZON 2 — EXPAND: Patient Intake Gateway (Months 7–18)

Product: add Pillar 1 (conversational AI intake, safety-veto, lab PDF extraction, 8-line pre-visit snapshot), built on the ClinPolisBot foundation.

GTM motion: upsell installed base — "your schedule is dense; now eliminate 60% of front-desk phone calls." +$100/MD/mo.

Data moat: Mayo Clinic Platform data lake (if accepted) trains the AI Urgency/Triage Engine.

Target: 1,000 practices, $15M ARR.

HORIZON 3 — LOCK-IN: Chart QA & RCM Guard (Months 19–36)

Product: add Pillar 3 (real-time E/M audit, 99213→99214 capture, HCC risk adjustment, denial interception), built on the artidoc-checker DAG architecture.

Moat completion: enterprise-grade value-based-care analytics for ACOs; churn → near zero.

Target: 3,000 practices, $54M ARR.

Cross-Horizon Enablers (continuous)

1. Compliance & Governance spine: BAAs from day one → HIPAA gap assessment (pilot) → SOC 2 Type II (Horizon 2) → ONC FHIR R4 / USCDI v4 certification posture (Horizon 3).

2. Founder IP & Asset Licensing: Formalize IP contribution / exclusive licensing agreements from founder to KVAN Health LLC for underlying core assets (Pillar 1 from ClinPolisBot, Pillar 2 from Kvann Flow, Pillar 3 from Synteris/artidoc-checker DAG) prior to closing accelerator SAFE or priced equity rounds.

3. FinOps asymmetry: hold ≤$0.01/encounter cost (multi-agent DAG routing) — protects >85% gross margin at every horizon.

4. Capital path: Pre-seed $110–160k via Cedars-Sinai ($100k/~3%), Mayo ($200k+ in-kind + data), OVF ($250k–$1M, Providence network via Joe); non-dilutive: MedTech Innovator, MassChallenge.

5. ROI proof engine: productize the Monte Carlo simulator as `calc.kvannhealth.com` — CFO-facing 3-minute ROI tool (feeds every sales motion).

6. Team & Hiring Gating: 70:30 AI:human execution model until seed. Zero pre-capital speculative hiring: first hire (part-time EHR/QA specialist, 10–15 hrs/wk) is gated strictly on either a signed pilot MoU/BAA with sandbox credentials or accelerator SAFE funding receipt.

Key Strategic Risks (long-term)

| Risk | Horizon | Mitigation |
| --- | --- | --- |
| OCHIN/Epic gatekeeping delays pilots | H1 | FHIR R4 abstraction layer → Athenahealth pivot is config, not rewrite |
| EHR vendors native-ify yield optimization | H2–H3 | Speed + Iron-Rule trust + marketplace entrenchment |
| AI triage regulatory exposure | H2 | Deterministic safety-veto layer; zero-millisecond red-flag override; no diagnostic claims |
| Founder bandwidth (single technical lead) | All | Accelerator capital → QA/fullstack hires before H2 |

Immediate Bridge

This document sets direction; all near-term execution lives in the tactical roadmap:

`_DEVELOPMENT/00_ADMIN/00.04_Roadmap_and_Budget/2026-09-14_KVANN_FLOW_TACTICAL_ROADMAP.md`.

Review cadence: quarterly, or upon any Horizon exit-criteria event.